## Andorid Customer app testing
Scenario | Action | Expected | Result | Remarks | Status
2019-01-09
Order history |  |  |  |  | ok
| Click order history | Show previous order | Previous order details displayed |  | ok
| Click home button | Home button available on the order history screen | No home button available |  | Not ok
| Click reorder | Show cart with order items | Working fine |  | ok
| Click Favourites | selection should be shown in favourites option on main page | No Changes Seen |  | Not ok
|  | click checkout | Showing Delivery screen | options : delivery now or take out required | Not ok
| Click continue to shop | Go to home screen | Goes to home Screen |  | ok
| Click checkout | Go to checkout screen or login screen if not signed in | Working fine |  | ok
| Enter coupon | Validate coupon code | Not working |  | Not ok
| Enter view offers | List of coupons shown | Working fine |  | ok
| Click on the coupon code | Coupon code transferred to checkout screen | The selected coupon is not transferred |  | Not ok
| Click delivery later | Request for delivery time | Working fine |  | ok
|  | Selected time should be displayed in the checkout screen | Working fine |  | ok
| Click on the delivery address | List of address from the user profile displayed | Working fine |  | ok
| Select a different delivery address | The new address is updated in the checkout screen | The address is not updated with the new address | Save option -Api Integration reqd | Not ok
| Click on proceed to payment | Display list of payment options | Working fine |  | ok
|  | The list of cards should display the nickname | To be tested once the new card functionality is working | Discussion
| Click on add new card | Card type selected automatically based on the first digit of the card number | Working fine |  | ok
|  | Expiry date cannot be in the past | Working fine |  | ok
|  | Enter CVV number | The number of digits on the CVV should be validated according to the card type Eg: 4 for Amex and 3 for the rest |  | ok
|  | Enter nickname | Cannot enter nick name |  | ok
| Click on place order | Display message order successful | Working fine |  | ok
My Weekly order | Click ok on the ok button on the order message | Go to home screen | Working fine |  | ok
| Click on my weekly orders | Show the details of the orders for the week | Working fine |  | ok
| Delete Option | Should delete only upcoming orders | Not working | Api Integration reqd | Not ok
My profile | Change contact information | Change profile picture | upload a profile picture -working | Save option -Api Integration reqd | ok
|  | Telephone number formated | formatted as XXX-XXX-XXXX and the country code 1 is set. | Save option -Api Integration reqd | ok
|  | Date of birth should be validated as more than 18 yrs. Of age Date should be formatted as MM/DD/YYYY | Working fine | Save option -Api Integration reqd | ok
|  | Click save to update the profile |  | Save option -Api Integration reqd | Not ok
Working fine
| Reset password | Ability to change the current password | Working fine | Submit option -Api Integration reqd | ok
|  | The password and confirm password should match | Not working | Submit option -Api Integration reqd | ok
| My delivery Locations | Display list of delivery address | Working fine |  | ok
|  | Display the default address to be used in my orders | None of the address are selected | Api Integration reqd | Not ok
|  | Office Delivery Location should be different from user personal Address listings |  | Api Integration reqd | Not ok
| Add a new address | The zip code should be validated (5 digits) | Not working |  | Not ok
|  | New address added | Not working |  | Not ok
| click payment methods | List of payment methods displayed | Working fine |  | ok
|  | Edit option | Not working
|  | Delete option | Not working
| Click on add new card | Card type selected automatically based on the first digit of the card number | Working fine |  | ok
|  | Card holder Name -number is also Accepted | Not working | Api Integration reqd | Not ok
|  | Card number -only 5 digit is also accepted | Not working | Api Integration reqd | Not ok
|  | Expiry date cannot be in the past | Working fine |  | ok
|  | Enter CVV number | The number of digits on the CVV should be validated according to the card type Eg: 4 for Amex and 3 for the rest |  | ok
|  | Enter nickname | enter nick name but number is accepted |  | Not ok
| Settings | List of settings displayed | Working fine | Api Integration reqd | ok
| Terms and conditions | Display terms and conditions | Working fine | need to provide data | ok
|  | Accept terms and conditions | Not working
New user registration |  |  |  |  | Not ok
| Phone entry | Telephone number formated | Formatted as XXX-XXX-XXXX if we donot enter country code 1. Normally users will not enter the country code 1. |  | Not ok
| Enter email id | Email id should be validated | Not getting validated |  | Not ok
| Mobile number | Formated
| Date of birth | Date of birth should be validated as more than 18 yrs. Of age Date should be formatted as MM/DD/YYYY | Age Validation ok Enter for Date search Required or option to enter Date required cumbersome to go back date to set from today | Change Date option for entry,best | Not ok
| Enter password | Password validation must be done (eg: First character is upper case, and there should a number or minimum 8 characters etc) | Not getting validated |  | Not ok
Not ok
Login | Google Login | Login ok,but Login Credentials Validation reqd |  |  | Not ok
| Face Book login | Login ok,but Login Credentials Validation reqd |  |  | Not ok
Not ok
| Forgot Password | email format validation and send mail confirmation to user | No validation and email sent to user |  | Not ok
Checkout page | Delivery Time 2 min later accepted | Not ok | Time validation |  | Not ok
Home screen | Register user | User id created | Not able to create a user id | Api Integration reqd | Not ok
| Scrolling of image | working fine
| Display shopping cart | Display shopping cart with order details | Not working | Api Integration reqd | Not ok
| Display filter | Display filter button with the previous selection | Not working | Api Integration reqd | not ok
| Display Alert | Display the alert icon | Not working | Api Integration reqd | not ok
| Restaurant Selection | multiple order selection | Not working | Api Integration reqd | not ok
|  | Not able to Select option -Why not try | Not working
Cart |  | Shopping cart not displayed | Not working | Api Integration reqd | not ok
| Add Toppings | choose upto 3 | working |  | ok
Delivery option | Restaurant Seletion | ok |  |  | ok
| Multiple items Seletion | Not working
| Shopping Cart | Seen,Add items to Cart ,if Continue to shop button is Clicked | not adding Items to Cart | Api Integration reqd | Not ok
Checkout page | Delivery Time 2 min later accepted | min time for delivery has to be set | Time validation |  | Not ok
why not try menu |  | click for selection of items | Not working |  | Not ok
Take Out | Restaurant Seletion | ok |  |  | ok
| Multiple items Seletion | Not working
| Shopping Cart | Seen,Add items to Cart ,if Continue to shop button is Clicked | not adding Items to Cart | Api Integration reqd | Not ok
Checkout page | Same Checkout page as Delivery Is seen | take out or take out later page should be displayed | Time validation |  | Not ok
Weekly Orders | Restaurant Seletion | ok |  |  | ok
| Multiple items Seletion | Not working
| Shopping Cart | Seen,Add items to Cart ,if Continue to shop button is Clicked | not adding Items to Cart | Api Integration reqd | Not ok
| Continue to Shop | Should go to weekly orders page for selection of other days | remains in Add items for the same day |  | Not ok
| Same Checkout page as Delivery Is seen | Delivery or take out page should be displayed | Time validation |  | Not ok
* | Selection of entire week | Check out Reqd Only after the Selection of entire week | Each day Check out |  | Not ok
Favourites |  | selection should be shown in favourites option on main page | No changes Seen | Api integration Reqd | Not ok
Filters | filter the option selected | show the filter option search | No changes Seen |  | Not ok
Notification | Show the notifications | working fine |  |  | ok

## Delivery boy testing
Scenario | Action | Expected | Result | Remarks | Status
Launch delivery app | Click on the app | Launches the app already logged in | Asking to login. | Will this login directly after first login | ok
How is the user registered, is it done from outside app or app is used to register first time
| Accept/ reject order | Confirmation Msg of Acceptance /rejection | Going to Order screen | Send msg with delivery boy Details to user and restaurant | Not ok
| Accept order | Show order details | Seeing more than one order | App must just display the details of the order | Not ok
| Order detail | Payment Type | Cash on Delivery | No Cash only Online payment | Not ok
| Click send push | Send notification to the customer that the order is accepted and provide delivery boy details to the customer | Nothing happens |  | Not ok
| Click live track | Open map app | Working fine |  | ok
| Scan QR code | Open camera to scan QR code | Not working | Might be issue with the emulator | Not ok
|  |  | Working fine |  | ok
|  |  | Email or push notification sent to the customer that the order is delivered | Not tested | Not ok
| Click upcoming order | All the pending orders displayed |  |  | ok
| Weekly delivery | All orders for the week is displayed | No Difference Seen Currently | Needs real data for testing | ok
| Click past order | All old orders displayed | Working fine |  | ok
| Double click on the order | Order details are displayed | Working fine |  | ok
Profile | Click on profile | Display profile | Working fine |  | ok
| Upload a photo | Provide option to upload a photo | Working fine |  | ok
| Phone Number | Validation and formatting Required |  |  | Not ok
| Click on edit | Fields are editable |  |  | ok
| Call office | Dial pre-set number for the office | opening call screen | Api Integration required | ok
| Logout | Logs out of the application | Working fine |  | ok

## Admin page
Options | Scenario | Action | Expected | Result | Remarks | 2019-01-09 | Comment
Login | Enter user name and password | Display Dashboard | Working fine |  | Ok
| Click on admin-Account profile | Display account profile |  |  | OK
| Upload a profile photo | Prompts for sellecting a picture to upload | Working fine | Can we add a link saying upload a photo below the profile pictureCurrent icon is not clearly visible | not ok | not ok
| Update profile info | Update name | Name updated |  | OK
|  | Update email | Can edit email id |  | not ok | not ok
Click on dashboard | Click on the tiles | Display detail report | Not responding | Waiting for API? | not ok | not ok
| Click on Recent restaurant list | view the details of pending Restaurant and approve or change status from active to deactive | Not responding |  | not ok | not ok
Cuisine | Add a new cuisine | Collect new cuisine info | Working fine |  | OK
| Upload cuisine picture | New picture uploaded | Working fine |  | OK
|  | Format and picture quality Check | Not working |  | not ok | not ok
| Activate cusine | Prompt to confirm | Working fine |  | OK
| Deactivate cuisine | prompt confirm | Working fine |  | OK
| Edit cuisine | Open info for editing | Working fine |  | OK
| delete cuisine | Delete the cuisine | Working fine |  | OK
| Search Cuisine | showing wrong entries | Not working |  | not ok | not ok
Website management | Change banner | Update banner and new banner is displayed on the customer app | option not available | Waiting for API? | not ok | not ok
| Change text | Update text and display new text in the customer app | option not available | Waiting for API? | not ok | not ok
Admin management | Add new admin | Collect admin info | admin created and email not sent | Will the email be sent? | not ok | not ok
| Delete admin | Popup confirming deletion | deletion |  | Ok
| Login to Admin | New active admin login granted | Working fine
Customer management | Click on customer management | List of customers should be shown | Working fine | Do we need a" Add new customer" button here, since we already have customer details from the customer app when the customer signs up.we will get the details from customer app right? | ok
| Click on activate customer | Pop up confirmation | Working fine |  | Ok
| click on deactivate customer | Pop up confirmation | Working fine |  | Ok
| Tracking of who added new customer info | Keep admin login and ip details | Not Sure |  | not ok | not ok
| status filter | show only active /deactive list | not working |  | not ok | not ok
Push email management | Click on Push email management | Display email and push notification templates | Working fine |  | Ok
| Send email | send email to customer /restaurants | Working fine
| Tracking of email sent info | list of email sent and login info | Not working |  | not ok | not ok
| send push notification button | notification format should be opened | Not working |  | not ok | not ok
| edit new customer email link | edit email template | Working fine | User signs up using the customer app should we display the password in the email body? Please change the text "login link " to "click here to login" also update the text" Password updation link" to "Update password" | not ok | not ok
| Welcome Mail | email template should be sent to new register customer /restaurants with login link and update password for forget password automatically | Not Sure | Testing reqd | not ok | not ok
Restaurant Management | List of restuarants |  | Working fine |  | Ok
| Status Active /deactive |  | Working fine |  | Ok
* | Pending Status Approval | Change status to active /reject | Not working |  | not ok | not ok
| delete/edit Restaurant info |  | Working fine
| Edit info -Zip code | validation | Not working |  | not ok | not ok
| Edit info -phone number | Formatting and validation | Not working |  | not ok | not ok
| Tax info | Mandatory | Not working |  | not ok | not ok
| Percentage entry | update percentage value | Working fine |  | ok | ok
History | Transaction history | Monthly and yearly as well as daily report needed | working fine | daily report required | not ok | not ok
| Receipt history |  | Working fine | real data for testing reqd | ok | ok
| Payment history |  | Working fine | real data for testing reqd | ok | ok
| Print |  | Working fine | real data for testing reqd | ok | ok
Revenue | List of restaurants |  | Working fine | real data for testing reqd | ok | ok
| print |  | Working fine | real data for testing reqd | ok | ok
Delivery Dispatcher | Account Profile | Name ,phone ,address Edit option | Working fine |  |  | ok
|  | Phone number and address formatting and validation reqd | Not working |  | Not ok | not ok
| New Delivery dispatcher creation | Phone number and address formatting and validation reqd | Working fine | Validation reqd | Not ok | Not ok
| Edit /delete |  | Working fine |  | ok | ok
| New User login in dispatcher link | successful | Working fine |  | ok | ok
All order
App Setting
Promo code
Setup payment Portal
Spell Change | Managment | Management |  |  | not ok | not ok | Done

## Vendor Page
Scenario | Action | Expected | Result | Remarks | 2019-01-09 | Comment
Dashboard | Click on total orders | Display order details | Display only? |  | 0k
| Click on products | Display product details | Display only? |  | 0k
| Click on total earnings | Display earnings details | Display only? |  | 0k
| Click on promocode | Display available promocodes | Display only? |  | 0k
| Account profile | Edit the details | Working fine |  | ok
|  | Phone number ,address,picture formatting reqd | No formatting |  | not ok
| change password | Check for current password and update new password | working fine
| logout |  | working fine |  | ok
My profile | Click on Account profile | Account profile displayed | Account profile displayed |  | ok
Revenue | Click on revenues | Display earnings details |  | Real data needed | ok | Dummy Data Added
| Print | open Print screen | working fine | Real data needed | ok | Dummy Data Added
Variant group | Add New Variant group | Succesfully added drinks |  |  | ok
| Delete variant group | Succesfully delete drinks |  |  | ok
Product | Add New product | Updated new product | Working fine |  | ok
| Edit the product | Edit the details | Working fine |  | ok
| Click on Active/deactive | Activated /deactivated | Working fine |  | ok
Orders | Scheduled |  | Not working | Real data needed | Not ok | in development
| Processing | Show the processing orders | working fine |  | ok
| Save to file excel and pdf | create files | working fine |  | ok
| Completed |  | Not working | Real data needed | Not ok | in development
| Trashed | Change to deleted /Rejected orders | Not working | Real data needed | Not ok | in development
Inventory | Click On edit | Edit the details | Working fine |  | ok
| search |  | Working fine |  | ok
Employee | Activate/Deactivate | Activated /deactivated | Working fine |  | ok
| Edit the employee details | Edited the employee details | Working fine
| Add new employee | Sucessfully add and active employee | Not sure ,Status Pending | Who will approve employees | ? Not ok | vender will add & approve Employee
Payment history |  |  | Don’t see any detials | Real data needed | ok/not ok | in development
Promocode | Add New promocode | New promocode added | Working fine |  | ok

## Dispatcher Panel
Options | Scenario | Action | Expected | Result | Remarks
Dashboard | Name ,phone ,address Edit option | Working fine |  |  | ok
| Phone number and address formatting and validation reqd | Not working |  | Not ok | not ok
| New User login | working fine |  |  | ok
| Change password | current password check | Update password |  | ok
| Reset Button | Not working |  | Not ok | Not ok
Orders | Click Each Options | Real data Needed for testing |  | Not ok | Not ok
Delivery Boy | create new delivery boy | working fine |  | ok | ok
| Edit | working fine |  | ok | ok
| Active /deactive | working fine |  | ok | ok
Assign order | Assign Order to deliver boys | Not working | Real Data needed |  | Not ok
Reports | Print or view Order Assigned details | Not working | Real Data needed |  | Not ok
Log out |  | working fine |  |  | ok

## Website page
Scenario | Action | Expected | Result | Remarks
Home | Search /find restaurants | search | Real data needed | Design testing phase only | ok
| Scrolling of images |  | ok | Design testing phase only | ok
| Listed Menu options | Delivery address | Change to delivery Location | Design testing phase only | Not ok
| Filter | Selection of filter |  | Design testing phase only | ok
|  | Edit preferred Address |  | Design testing phase only | Not ok
| Shopping cart | Click -take to check page | goes to Add to cart page | Design testing phase only | Not ok
| Add to cart | Check out page - Add new Address | Working fine | Design testing phase only | ok
| Add new address | email id should be validated | Working fine | Design testing phase only | ok
|  | Phone and Zip code,address validation reqd | not working | Design testing phase only | Not ok
| Combo offers |  | Not working | Design testing phase only | Not ok
Weekly Planner | Days selection | click on selected days | not working | Design testing phase only | Not ok
Design testing phase only
Delivery | Selection of Restaurants and menu | Selection working | moving to cart and checkout ,but additional recommedations not working | Design testing phase only | ok
| Continue shopping | go back to restaurant menu | go to weekly planner | Design testing phase only | Not ok
| check out | deliver now or later page | go to check out page | Design testing phase only | ok
|  | view offers | not working | Design testing phase only | Not ok
| Favourites | not working | not working | Design testing phase only | Not ok
| View offers | not working | not working | Design testing phase only | Not ok
| Payment option | Payment option | Multiple payment option selected |  | Not ok
| Amount | Calculation not Correct | Amount validation required |  | Not ok
Takeout | Selection of Restaurants and menu | Selection working | moving to cart and checkout ,but additional recommedations not working | Design testing phase only | ok
| Continue shopping | go back to restaurant menu | go to weekly planner | Design testing phase only | Not ok
| check out | Take out or take out later page | not working | Design testing phase only | Not ok
|  | view offers | not working | Design testing phase only | Not ok
| Favourites | not working | not working | Design testing phase only | Not ok
| View offers | not working | not working | Design testing phase only | Not ok
| Payment option | Payment option | Multiple payment option selected |  | Not ok
| Amount | Calculation not Correct | Amount validation required |  | Not ok
Favourite | Reorder | Selection of items and checkout | Not working |  | Not ok
Restaurant Partners | Restaurent name | Spell correction |  |  | Not ok
| Email and phone number validation | validation reqd |  | Design testing phase only | Not ok
| Submit button |  |  | Api integration reqd | ok
Delivery address |  | change to Delivery location |  |  | not ok
Design testing phase only
Design testing phase only
Profile | Open profile page | Edit info and save details | Api integartion reqd | Design testing phase only | Not ok
|  | Phone number formatting | letters accepted | Design testing phase only | Not ok
|  | Profile photo update | Not working | Design testing phase only | Not ok
|  | Reset Password | Not working | Design testing phase only | Not ok
Payment Methods | Open Payment details | only card details are shown | Not working | Design testing phase only | Not ok
|  | Edit /delete should work | Not working | Design testing phase only | Not ok
|  | Card number formatting and validation | Not working | Design testing phase only | Not ok
|  | Save option | Not working | Design testing phase only | Not ok
|  | Month and CVV Validation | Not working | Design testing phase only | Not ok
Order History | Filter option | No alignment |  | Design testing phase only | Not Ok
| Date Search | Validation reqd | Future and older date accepted | Design testing phase only | Not Ok
| Reorder button | show details | Not working | Design testing phase only | Not Ok
Design testing phase only
Change location | Open Address Page | Edit details | Validation not working | Design testing phase only | Not ok
| Save option |  |  | Design testing phase only | Not ok
Design testing phase only
Login | open login details page | working fine |  |  | ok
| Register |  | Not working | Design testing phase only | Not ok
| FB Login |  | Not working | Design testing phase only | Not ok
| google Login |  | Not working | Design testing phase only | Not ok
| Forgot password |  | Not working | Design testing phase only | Not ok
| Login |  | Not working | Design testing phase only | Not ok
Design testing phase only
Register | entry login details | working fine |  | Design testing phase only | ok
Subcribe | Entry email address | Subcription message and unscbscribe button | Not working | Design testing phase only | ok